## Schedule
Serial Number | Category | Description | Depends On | Status | Complexity | Days | Start Date | End Date | Assignee | Progress % | Integration Effort | Fixed Start Date | Key Milestone | Epic
1 | Design | Research user needs |  | Completed | M | 4 |  |  | Alice | 100 |  |  |  | https://example.atlassian.net/browse/WEB-101
2 | Design | Wireframes and design system | 1 | In Progress | L | 6 |  |  | Alice | 60 |  |  |  | https://example.atlassian.net/browse/WEB-101
3 | Backend | Content API |  | In Progress | L | 8 |  |  | Ben | 40 |  |  |  | https://example.atlassian.net/browse/WEB-102
4 | Backend | Add tests for content API | 3 | Open | M | 3 |  |  | Ben | 0 |  |  |  | https://example.atlassian.net/browse/WEB-102
5 | Backend | Search service | 3 | Open | L | 7 |  |  | Chen | 0
6 | Frontend | Page templates | 2 | Open | L | 8 |  |  | Dana | 0 |  |  |  | https://example.atlassian.net/browse/WEB-103
7 | Frontend | Search UI | 5,6 | Open | M | 4 |  |  | Dana | 0
8 | Frontend | Add tests for search UI | 7 | Open | S | 2 |  |  | Chen | 0
9 | Backend | Content migration | 4 | Open | M | 5 |  |  | Ben | 0
10 | QA | Beta release | 7,9 | Open | S | 2 |  |  | Chen | 0 |  |  | true | https://example.atlassian.net/browse/WEB-104
11 | QA | Accessibility review | 10 | Open | M | 3 |  |  | Alice | 0
12 | Launch | Performance tuning | 10 | Open | M | 4 |  |  | Ben | 0
13 | Launch | Launch announcement |  | Open | M | 3 |  |  | Alice | 0 |  | 2026-10-19 |  | https://example.atlassian.net/browse/WEB-106
14 | Launch | Public launch | 11,12,13 | Open | S | 2 |  |  | Dana | 0 |  |  | true | https://example.atlassian.net/browse/WEB-105
15 | Frontend | Analytics dashboard |  | Open | M | 4 |  |  |  | 0

## Session
GANTT SESSION DATA — import this file to restore your work
PROJECT NAME | Website Relaunch
PROJECT START | 2026-09-07
THEME | dark
RESOURCES
Alice
Ben
Chen
Dana
PUBLIC HOLIDAYS
2026-10-12
VACATION DAYS | Person | Date
| Ben | 2026-10-05
| Ben | 2026-10-06
| Dana | 2026-10-19
ASSIGNMENTS | Serial Number | Assignee
| 1 | Alice
| 2 | Alice
| 3 | Ben
| 4 | Ben
| 5 | Chen
| 6 | Dana
| 7 | Dana
| 8 | Chen
| 9 | Ben
| 10 | Chen
| 11 | Alice
| 12 | Ben
| 13 | Alice
| 14 | Dana
PROGRESS | Serial Number | Percent
| 1 | 100
| 2 | 60
| 3 | 40
| 4 | 0
| 5 | 0
| 6 | 0
| 7 | 0
| 8 | 0
| 9 | 0
| 10 | 0
| 11 | 0
| 12 | 0
| 13 | 0
| 14 | 0
| 15 | 0
STATUSES | Serial Number | Status
| 1 | Completed
| 2 | In Progress
| 3 | In Progress
| 4 | Open
| 5 | Open
| 6 | Open
| 7 | Open
| 8 | Open
| 9 | Open
| 10 | Open
| 11 | Open
| 12 | Open
| 13 | Open
| 14 | Open
| 15 | Open
FIXED START DATES | Serial Number | Date
| 13 | 2026-10-19
MILESTONES | Serial Number
10
14

## Workload
Person | Tasks | Total Days | Finishes