## Sheet1
Serial Number | Category | Description | Depends On | Status | Complexity | Days | Start date | End date | Assignee | Integration Effort
1 | DESIGN | To evaluate a finalize design approach for object storage library | 0 | Completed | L | 8 |  |  | Alice | Yes
2 | DESIGN | Create module structure for object storage library | 0 | Completed | S | 3 |  |  | Alice | Yes
3 | DESIGN | Design user façade interface and models | 0 | In Progress | L | 8 |  |  | Alice | Yes
4 | RESEARCH | Research ticket for exploring capability to implement map overrides for config for AWS SDK | 0 | Completed | L | 8 |  |  | Alice | Yes
5 | RESEARCH | Research Checksum Support in AWS SDK with Netty | 0 | Completed | S | 3 |  |  | Alice | Yes
6 | RESEARCH | Research AWS SDK support for S3 Signature Versions (v2 & v4) | 0 | Completed | S | 3 |  |  | Alice | Yes
7 | RESEARCH | Research Pagination Support in AWS SDK with Netty | 0 | Completed | S | 3 |  |  | Alice | Yes
8 | RESEARCH | Research Proxy Support in AWS SDK with Netty | 0 | Completed | S | 3 |  |  | Alice | Yes
9 | RESEARCH | Research S3 Range Request Support in AWS SDK with Netty | 0 | Completed | S | 3 |  |  | Alice | Yes
10 | RESEARCH | Research a Document TLS Certificate Verification Disabling in AWS SDK with Netty | 0 | Completed | S | 3 |  |  | Alice | Yes
11 | RESEARCH | Research credentials per request in AWS SDK with Netty. | 0 | Completed | S | 3 |  |  | Alice | Yes
12 | RESEARCH | Research general logging a logging of request headers in AWS SDK. | 0 | Completed | S | 3 |  |  | Alice | Yes
13 | RESEARCH | Research settpUserAgent() in BlobStoreContextFactory for in AWS SDK with Netty. | 0 | Completed | S | 3 |  |  | Alice | Yes
14 | RESEARCH | Research tier based strategy , research on glacier tolerance in in AWS SDK with Netty. | 0 | Completed | M | 5 |  |  | Alice | Yes
1 |  |  | 1 | open | L |  |  |  | Ben | Yes
2 |  |  |  |  | S |  |  |  | Chen | No
17 | CORE IMPLEMENTATION | To implement the configuration layer for object storage library | 0 | Completed | L | 8 |  |  | Alice | Yes
18 | CORE IMPLEMENTATION | To implement the AWS SDK Netty Config for object storage library | 0 | Completed | L | 8 |  |  | Alice | Yes
M
71 | TESTING | Test plan using test suite for every vendor | 69 | Open | L | 8 |  |  |  | No
73 | JCLOUDS TESTING | Investigate Hitachi Object Storage S3 Compatibility | 68 | Open | M | 5 |  |  |  | No
74 | MISC | Add code coverage to object storage test job suite in Jenkins(Sonarqube not needed) | 0 | Open | S | 3 |  |  |  | No
75 | MISC | Validate multipart uploads usage in the existing codebase. | 0 | Open | S | 3 |  |  |  | No
76 | TESTING | Performance testing of every operation in is library VS Jclouds | 71 | Open | L | 8 |  |  |  | No
77 | TESTING | Create Test Suite for the library | 0 | Completed | L | 8 |  |  |  | No
78 | CORE IMPLEMENTATION | Implement Spring Boot Starter for Object Storage Library | 0 | Open | L | 8 |  |  |  | No
79 | SECURITY | CVE scan of the library | 0 | Open | S | 3 |  |  |  | No